## README
Last Update | 2019-04-18
Author | Zhijia Zhao / Manu Sridharan
Email | manu@cs.ucr.edu
Description | This is a SCRUM template designed for project managment in CS180. Replace this section with YOUR TEAM information
Summary / Requirements | This spreadsheet serves two purposes: (1) for your team to track progress during your sprints, and (2) as a record of what user stories were implemented, in which tasks, and by whom. For (1), if you prefer to use an alternate tool to track progress as you go (e.g., Trello), that is fine. However, for (2), it is critical that you keep the "Product Backlog" and "Archives" up to date, at least at the end of each sprint. Also, note that if the number of estimated points for a story ends up being very inaccurate (i.e., if the user story took much more or much less effort than expected), please update the story points estimate and give a comment explaining the adjustment.
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means to be "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Perform task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | Authentication | As an unregistered customer who is interested in the app, I want to register an account so that I can login the app and login with user nam and password, and logout to end the session | 3 | 1
3 | See # of Available Parking | As a student, I want to be able to see the number of available spaces in all UCR parking lots. | 2 | 3
2 | Profile | As a student, I want to set my account's profile preferences, schedule, and permit information. | 2 | 2
4 | Parking Recommendations | As a student, I want to input my first class of the day to get recommendations on where to park. Saving my class schedule will make it more convenient since we only have to add the classes one time. I want to know how long it takes to walk to class from the parking lot. | 6 | 5
6 | If Full | As a student, I want to get warnings about full parking lots and get the next ideal lot. It should check the available spots and recommend the next available spot if available spots are taken. | 5 | 6
7 | Dashboard | As a student, I want to be able to see all the important information regarding parking at UCR. It should show the best choices given based on rank, permit expiration time, navigation. | 4 | 7
8 | Notifications | As a student, I would want notifications about important things I need to know. Notifications can be turned on/off. I can choose how long before my class to get notifications. An alert will be sent if parking time is close to expiring or if permit is expiring. | 8 | 9
5 | Navigate | As a student, I want to be able to get directions to the recommended parking lot. By clicking on notification or a button, it should give directions on how to get there. | 5 | 8
9 | Lot Information | As a student, I want to access information about the location of the parking lot and which building(s) are nearby | 2 | 4
| Total |  | 37

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Task 1: Register (Anthony)
Task 2: Login (Anthony)
Task 3: Logout(Daniel)
Task 4: Implement DB for Accounts (Daniel)
Task 5: Screen After Login(Dylan)
Task 6: Profile Page(Aaron)
Task 7: Update Profile Schedule, Permit(Marios)
Task 8: Update Profile Preferences(Marios)
Task9: Display Parking Recommendation(Dylan/Daniel)
Task 10 : Saving Class Schedule(Marios)
Task 11 : Walking time(Anthony)
Task 12: Lot spaces(Aaron)
Task13: Building(s) near lot(Anthony)
Task14: Directions(Anthony)
Task15 : link recommended lot to its lot info page(Anthony)
Task16: display permit type and expiration in dashboard(dylan)
Task17: Recommend next closest lot(Marios)
Task18: Warnings for full lots(Marios)
Task 19: UI improvement(anthony)
Task20: Notifications page(Aaron/Daniel)
Task 21: Notifications before class(Daniel/Aaron)

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 |  | Task 1: Register (Anthony)
Task 2: Login (Anthony)
Task 3: Logout(Daniel)
Task 4: Implement DB for Accounts (Daniel)
Task 5: Screen After Login(Dylan)
Task 6: Profile Page(Aaron)
Task 7: Update Profile Schedule, Permit(Marios)
Task 8: Update Profile Preferences(Marios)
2 |  | Task9: Display Parking Recommendation(Dylan/Daniel)
Task 10 : Saving Class Schedule(Marios)
Task 11 : Walking time(Anthony)
Task 12: Lot spaces(Aaron)
Task13: Building(s) near lot(Anthony)
Task14: Directions(Anthony)
Task15 : link recommended lot to its lot info page(Anthony)
3 |  | Task16: display permit type and expiration in dashboard(dylan)
Task17: Recommend next closest lot(Marios)
Task18: Warnings for full lots(Marios)
Task 19: UI improvement(anthony)
Task20: Notifications page(Aaron/Daniel)
Task 21: Notifications before class(Daniel/Aaron)

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 37 | 0 | 0 | 37 | 37
1 | 37 | 5 | 5 | 32 | 24.6667
2 | 37 | 15 | 20 | 17 | 12.3333
3 | 37 | 17 | 37 | 0 | 0